## general_report
Issue Type | Key | Summary | Description | Status | Resolution | Created | Updated | File Number | Game Name | Failed Regulation Number | Failed Regulation Text | Supplier Response | GLI Response
Bug | FLT-6 | Missing information for "有效投注额" (valid bets) on helpscreen. | GLI has noticed that there is a "有效投注额" column in game history. However, there is no related description on help screen about this item and it is confused to the player. | Initial - EN | Unresolved | 2015-05-06 06:00 | 2015-05-07 22:15 | MO-339-FLT-15-01 | Baccarat | 4 (c) | 4. The System must be able to display for each Game or Lottery, as the case may be, the following information on the current page or on a page directly accessible from the current page via a hyperlink. (c) instructions on how to play, including a pay-table for all prizes and special features; | 已經在說明頁面加上"有效投注額計算方式"
Bug | FLT-5 | Missing RTP information. | GLI has noticed that there is no RTP information in game. | Initial - EN | Unresolved | 2015-05-05 23:41 | 2015-05-07 22:31 | MO-339-FLT-15-01 | Baccarat | 1 (b) | 1. The System must: (b) provide over specified periods no more than the house advantage (if any) agreed by the Commissioners with the Operator; and | RTP information 已經加上
Observation | FLT-4 | The game will not display the winning message if there is no net win | GLI has noticed that there would be displayed a "彩金" box (winning message) about shows the game net win amount for each completed game. However, when there is no net win for the game, the "彩金" box (winning message) will not display and there is no other method to clearly show how much the game is lost(or Tie) clearly. Please refer to attached screenshot for the reference. This case has not conflict the jurisdictional requirements. So it categorized as an "Observation" only and will not affect GLI's testing and game results. | Initial - EN | Unresolved | 2015-05-05 06:21 | 2015-05-06 22:25 | MO-339-FLT-15-01 | Baccarat |  |  | 這是刻意設計的結果
Bug | FLT-3 | The game results may not be displayed during game play | During actual game play, GLI has noticed that if the dealer used a long time to input the game result, the system may have the chance to miss the game result information. Please refer to the attachment screenshot for further information. The card result couldn't be displayed in this game, even the game were at the complete stage. | Initial - EN | Unresolved | 2015-05-05 06:10 | 2015-05-07 23:38 | MO-339-FLT-15-01 | Baccarat | 1 (c) | 1. The System must: (c) integrate contingencies for loss of continuity of play; | 現場作業流程會避免這種情況發生 牌局進行時間過長時,控管人員將會進行 void game 程序
Observation | FLT-2 | Bet banker win result in "super six" pay 0.5 to 1 is not mentioned on game table. | GLI has noticed that when the game result is "super six", the banker bet will not pay by 1 to 1, it pay by 0.5 to 1. This is mentioned in game rule(help screens). However, on the game table( attachment) it only mentioned "pay by 1 to 1( 庄 免佣 1:1)", player may be confused with it. | Initial - EN | Unresolved | 2015-05-05 04:24 | 2015-05-07 23:28 | MO-339-FLT-15-01 | Baccarat |  |  | 相關資訊已修正
Bug | FLT-1 | Missing game information on helpscreen. | GLI has noticed that there is some information missing on help screen as below. #1. The help screen has not mention whether joker cards are used for the game or not. Besides, no card shuffle and sequence of card deal description. #2. No description for network disconnected condition and in-completed game. #3. The help screen has not mentioned when player and banker both got same value 8 points (or 9 points) at first two cards, it would be a tie game. #4. There is no "非免佣" (no commission) choice in game but the help screen has related description. | Initial - EN | Unresolved | 2015-04-27 23:44 | 2015-05-08 02:35 | MO-339-FLT-15-01 | Baccarat | 1. (a) | 1. The System must: (a) follow the rules for Online Gambling published to the Participant or potential Participant prior to its placing any sums with the Operator for participation in Online Gambling; and, | 已修正